KODIVIAN TECHNOLOGIES LLP

ISO 27001 Certified  |  A SS Group Company

CHANGE REQUEST

& Implementation Proposal

Bulk Statement-Processing Pipeline – Batch Upload, Auto-Matching & Job Tracking

Delivered Functional Scope beyond the approved SRS (Release 1.1)

Scheme Management System & Stock Statement Entry Automation

| Document Control |  |
| --- | --- |
| Document Name | Change Request – Bulk Statement-Processing Pipeline |
| CR Reference No. | KT/STED/CR-03 |
| CR Report Item | CR-03 (CR Report) |
| Classification | New Module |
| Release No. | 1.0 |
| Date of Release | 3rd July 2026 |
| Client | Stedman Pharmaceuticals |
| Prepared By | Kodivian Technologies LLP |
| Reviewed By | Vijay Sabari |
| Approved By | ________________________ |
| Approved Date | ________________________ |

# 1. Purpose of this Change Request

This Change Request is raised by Kodivian Technologies LLP for Stedman Pharmaceuticals to formally document, scope, estimate and obtain approval for the Bulk Statement-Processing Pipeline delivered in the Scanify portal. This item corresponds to Change Item CR-03 in the CR Report.

The SRS (Rel. 1.1) described single-file statement upload only. The delivered portal adds a batch/asynchronous processing subsystem with automated file-to-stockist matching and job tracking. This CR captures that additional module for formal re-baselining and commercial settlement.

# 2. Background & Context

During high-volume months, statements arrive in large numbers. Uploading and tagging them one at a time is slow and error-prone.

The delivered subsystem lets an operator upload a single archive containing many statements, create a bulk job, and process the whole batch in the background with live status and a paginated job list, with filenames automatically matched to the correct stockist.

SRS baseline vs. delivered capability:

| SRS Baseline (Rel. 1.1) | Delivered in the Portal |
| --- | --- |
| Individual file upload (JPG/PNG/PDF/Excel/Word/txt) tagged by Stockist, Region and Month-Year, then single-statement extraction. | Upload a single archive (ZIP) of many statements, create a bulk job, and process the whole batch in the background. |
| Manual stockist tagging per file. | Automatic filename-to-stockist matching, with suggestions surfaced for files that cannot be matched confidently. |
| No batch tracking. | Live status polling and a paginated job list – New Bulk Job, Bulk Processing Jobs, Bulk Job View (create, view, delete). |

# 3. Business Justification (Reason for Change)

Batch processing removes a major operational bottleneck that the single-file SRS flow could not address:

High-volume months can be processed by uploading one archive rather than dozens or hundreds of individual files.

Automatic filename-to-stockist matching removes repetitive manual tagging and reduces mis-tagging.

Background processing with live status keeps operators productive while large batches run.

A job list with create/view/delete gives clear operational control over batches.

Batch/asynchronous processing and automated file-to-stockist matching are beyond the single-file flow in the SRS and are therefore raised as a formal net-new module.

# 4. Proposed Change – Delivered Capability

The delivered Bulk Statement-Processing Pipeline provides the following capabilities in the portal:

| Capability | Description |
| --- | --- |
| Archive intake | Upload a single ZIP containing many statements and create a bulk job. |
| Background processing | Process the whole batch in the background with live status polling. |
| Auto-matching | Automatic filename-to-stockist matching, with suggestions for files that cannot be matched confidently. |
| Job management | New Bulk Job, Bulk Processing Jobs (paginated list) and Bulk Job View – create, view and delete jobs. |

# 5. Scope of Work

5.1 In Scope

Design of the bulk-job data model and ZIP ingestion.

Background processing pipeline with live status polling.

Automatic filename-to-stockist matching, with suggestions for unmatched files.

New Bulk Job screen; paginated Bulk Processing Jobs list; Bulk Job View (create/view/delete).

Integration with the existing extraction and validation flow for each statement in the batch.

Functional and high-volume testing and UAT support.

5.2 Out of Scope

Changes to the single-statement extraction/validation logic beyond wiring it into the batch pipeline.

Data cleansing or correction of pre-existing master/transactional data-quality issues.

Ongoing production support / AMC, which can be covered under a separate support agreement.

Any new functional change or scope expansion requested after sign-off, which will be raised as a separate CR.

# 6. Delivery Approach & Methodology

The subsystem was delivered in a controlled, phased manner:

| Phase | Key Activities |
| --- | --- |
| Phase 1 – Intake & Model | Bulk-job model; ZIP ingestion; background processing pipeline. |
| Phase 2 – Matching | Automatic filename-to-stockist matching with confidence and suggestions for unmatched files. |
| Phase 3 – Screens | New Bulk Job, Bulk Processing Jobs list and Bulk Job View with live status. |
| Phase 4 – Integrate | Wire the batch into per-statement extraction and validation. |
| Phase 5 – Validate | High-volume testing and UAT support. |

# 7. Detailed Effort Estimation

The total estimated effort for this change is 5 (five) person-days. The breakdown is as follows:

| Stage | Focus | Activities |
| --- | --- | --- |
| Day 1 | Intake & pipeline | Bulk-job model; ZIP ingestion; background processing pipeline. |
| Day 2 | Auto-matching | Filename-to-stockist matching with confidence; suggestions for unmatched files. |
| Day 3 | Job screens | New Bulk Job; paginated Bulk Processing Jobs list; create/view/delete. |
| Day 4 | Job view & polling | Bulk Job View with live status polling; integration with extraction/validation. |
| Day 5 | Testing & handover | High-volume testing, UAT support and handover. |

Total Effort: 5 person-days.

Effort is expressed in person-days of dedicated engineering work and reflects the design-and-build effort delivered beyond the SRS baseline, presented here for formal approval and commercial settlement.

# 8. Indicative Timeline

Subject to written approval of this CR, the effort is represented as a continuous 5 working-day engagement.

| Milestone | Target |
| --- | --- |
| CR approval & inputs received | Day 0 |
| Intake & pipeline ready | End of Day 1 |
| Auto-matching available | End of Day 2 |
| Job screens available | End of Day 3 |
| Live status & integration complete | End of Day 4 |
| High-volume testing, UAT & sign-off | End of Day 5 |

# 9. Commercials – Implementation Fee

This is a one-time change request with an associated implementation fee for the 5 person-days of design and build effort described above.

| # | Description | Effort | Amount |
| --- | --- | --- | --- |
| 1 | Design and delivery of the Bulk Statement-Processing Pipeline (ZIP batch upload, background processing, automated file-to-stockist matching and job tracking). | 5 person-days | ₹ ____________ |
|  | One-time Implementation Fee (Total) | 5 person-days | ₹ ____________ |

Amounts are to be finalised and are shown as placeholders pending commercial confirmation.

Taxes (GST) as applicable will be charged additionally.

This capability has already been designed and delivered in the portal; this CR formalises and re-baselines it in line with the CR Report recommendation.

# 10. Assumptions & Client Dependencies

The capability described has been reviewed against the delivered portal and the CR Report (Delivered Scope vs. SRS).

Client-side stakeholders are available to review the delivered functionality and provide sign-off.

No further functional change or scope expansion is introduced under this CR beyond what is already delivered.

Existing master and transactional data required by this capability is available and reasonably clean.

Statement filenames follow a convention that allows reasonable stockist matching; unmatched files are handled via suggestions.

# 11. Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Incorrect file-to-stockist matching | Confidence-based matching with suggestions and operator confirmation for low-confidence files. |
| Long-running batches affecting responsiveness | Background processing with live status; batch isolated from interactive use. |
| Partial-batch failures | Per-file status in the job view so failures are visible and can be re-processed. |

# 12. Deliverables

A working bulk pipeline: New Bulk Job, Bulk Processing Jobs list, Bulk Job View.

Background batch processing with live status polling.

Automatic filename-to-stockist matching with suggestions for unmatched files.

UAT sign-off of the batch flow.

# 13. Acceptance Criteria

A ZIP of many statements can be uploaded and processed as a single background job.

Filenames are matched to the correct stockist, with suggestions for unmatched files.

Job status, pagination and create/view/delete behave correctly.

# 14. Approval & Sign-off

By signing below, both parties agree to the scope, effort and commercial terms set out in this Change Request.

| For Kodivian Technologies LLP | For Stedman Pharmaceuticals |
| --- | --- |
| Name: ____________________________ | Name: ____________________________ |
| Designation: ______________________ | Designation: ______________________ |
| Signature & Date: __________________ | Signature & Date: __________________ |

— End of Change Request —